## Sheet1
Risk | Outcome | Responsility | Impact | Likelihood | Risk factor | Control/Mitigation | Reponse | Impact | Lieklihood | Risk Factor
Customer Payment details breached | Damage to company reputation, financial loss to customer | Developers | 5 | 3 | 15 | Dont save details, encrypt traffic so details cannot be intercepted, third party api like stripe and off load it to them | Inform the customer, prevent other customers to use the website from making payments until issues is resolved, fix breach, inform relevant authorities | 4 | 2 | 8
Customers Order details breached | Damage to company reputation, backlog on orders | Developers | 5 | 2 | 10 | Get download for all orders as a backup on the cloud, so information of orders can be stored as a back up | Inform the cloud provider to get the backed up information, block any further orders until issue is sorted | 5 | 1 | 5
Customer Personal information breached | Damage to company reputation, customer information leaked | Developers | 5 | 3 | 15 | Encrypt data so details cannot be intercepted | Inform the customer, prevent other customers to use the website. | 5 | 2 | 10
Developers losing work from GIT | Damage to company reputation, delay to client | Developers | 5 | 4 | 20 | Always have a backup in the cloud. Save as you go along. | Infrom team, try recover the files/codes ASAP. Inform the client if delays are expected. | 5 | 3 | 15